## UMOBILE calendar
UMOBILE CALENDAR
M.. | Project Month | Meeting | Deliverable | Milestone | Report | Additional events
M1 | February 2015 | Kick off meeting | - | MS1 Kick off meeting | - | Project presentation within SITI/Copelabs
|  |  |  | MS11 Public & Internal website has been set up |  |  | √
M2 | March 2015 | teleconference: 26/3/15 | - | - | - | 25/3/15 Future Internet Architectures Cluster | √
M3 | April 2015 | teleconference: 30/4/15 | D1.1 Project Handbook | - | - |  | √
M4 | May 2015 | teleconference: 28/5/15 | - | - | 3monthly report for: M1 to M3 | MobiSys DIYNetworking 2015 WWIC 2015 | √
M5 | June 2015 | teleconference: 25/6/15 | D2.1 End-user requirements report | - | - | COPELABS Openday event Cosener's 2015 | √
M6 | July 2015 | teleconference: 30/7/15 | D1.2 External Liaison Overview | MS12 Dissemination Plan available | - | ICNRG&IRTF GAIA meeting | √
D6.1 Dissemination plan
D6.10 Data Management Plan
M7 | August 2015 | - | - | - | 3monthly report for: M4 to M6 |  | √
M8 | September 2015 | teleconference: 24/9/15 | - | - | - |  | √
M9 | October 2015 | teleconference: 29/10/15 | - | - | - | ICT 2015, ICN 2015, ICNRG meeting, | √
M10 | November 2015 | teleconference: 26/11/15 | - | - | 3monthly report for: M7 to M9
M11 | December 2015 | 2nd physical meeting: 09-10/12/15-teleconference: 24/12/15 | - | - | -
M12 | January 2016 | teleconference: 28/1/16 | D3.3 UMOBILE ICN layer aabstraction initial specification | - | -
D4.1 Flowlet Congestion Control-Initial Report
D6.6 Standardisation Plan
M13 | February 2016 | teleconference: 25/2/16 | - | - | 3monthly report for: M10 to M12
M14 | March 2016 | teleconference: 31/3/16 | D2.2 System and Network requirement specifications | MS3 End-user and system requirements defined | -
2nd project meeting (DUTH?)
M15 | April 2016 | teleconference: 28/4/16 | - | - | -
M16 | May 2016 | teleconference: 26/5/16 | D3.1 UMOBILE architecture report |  | 3monthly report for: M13 to M15
M17 | June 2016 | teleconference: 30/6/16 | - | - | 1st periodic report
M18 | July 2016 | teleconference: 28/7/16 | D1.3 Project Management reports | - | 1st periodic report
D6.2 Dissemination Report
D6.4 Exploitation Plan
M19 | August 2016 | teleconference: 25/8/16 | - | - | 3monthly report for: M16 to M18
M20 | September 2016 | teleconference: 28/9/16 | - | - | -
M21 | October 2016 | teleconference: 27/10/16 | - | - | -
3d project meeting ?
M22 | November 2016 | teleconference: 24/11/16 | - | - | 3monthly report for: M19 to M21
M23 | December 2016 | teleconference: 29/12/16 | - | - | -
M24 | January 2017 | teleconference: 26/1/17 | D4.2 Flowlet Congestion Control- Final Report | - | -
D4.3 Name-based Replication Priorities
D5.1 Validation methodology and evaluation report
D5.3 Proof of Concept
M25 | February 2017 | teleconference: 23/2/17 | - | - | 3monthly report for: M22 to M24
M26 | March 2017 | teleconference: 30/3/17 | - | - | -
M27 | April 2017 | teleconference: 27/4/17 | - | - | -
4th project meeting ?
M28 | May 2017 | teleconference: 25/5/17 | D4.4 Set of QoS interfaces and algorithms | - | 3monthly report for: M25 to M27
M29 | June 2017 | teleconference: 29/6/17 | - | - | -
M30 | July 2017 | teleconference: 27/7/17 | D2.3 System and Network requirement specifications | MS4 Requirements of the validation scenarios defined | -
|  |  | D2.4 System and Network Deployability Design | MS5 UMOBILE ICN layer abstraction specifications have been defined
|  |  | D3.2 UMOBILE architecture report | MS6 UMOBILE architecture implemented
|  |  | D3.4 UMOBILE ICN layer abstraction final specification | MS7 QoS interfaces and mechanisms for data handling have been integrated within UMOBILE platform
|  |  | D4.5 Report of data collection and inference models | MS8 Flowlet Congestion Control Developed
M31 | August 2017 | teleconference: 31/8/17 | - | - | 3monthly report for: M28 to M30
M32 | September 2017 | teleconference: 28/9/17 | - | - | -
M33 | October 2017 | teleconference: 26/10/17 | - | - | -
M34 | November 2017 | teleconference: 30/11/17 | D5.4 Proof-of-Concept | MS14 Workshop on UMOBILE project organised | 3monthly report for: M31 to M33
5th project meeting?
M35 | December 2017 | teleconference: 28/12/17 | D6.7 Standardisation report | MS13 contribution to standards reported
M36 | January 2018 | teleconference: 25/1/18 | D1.4 Project Management reports | MS2 End of Project | 3monthly report for: M34 to M36
D5.2 Validation methodology and evaluation report
|  |  | D5.5 Report on the validation of the deployment trial | MS9 Integration completed, system evaluated and proof-of-concept is available
D6.3 Dissemination Report
|  |  | D6.5 Exploitation report | MS10 Deployment trial successfully completed
D6.8 Awareness and Wider Societal Implications
D6.9 Final plan for the Use and Dissemination of Foreground
M37 | February 2018 | teleconference: 25/2/18 |  |  | Periodic & Final report
M38 | March 2018 | teleconference: 29/3/18 |  |  | Periodic & Final report